## Folha1
Sprint Backlog
Forecast | ToDo | In-Progress | Done
Detect code smells | Member 1: gui package Member 3: model package Member 4: preferences package Member 5: cli package | Member 1: detecting smells Member 5: detecting smells | Member 5: finished code smells. Member 1: finished code smells. Member 2: finished code smells.
Use Case Diagrams | Member 1: gui package Member 2: logic package Member 3: model package Member 4: preferences package Member 5: cli package | Member 2: making diagrams
Design patterns | Member 1: gui package Member 2: logic package Member 3: model package Member 4: preferences package Member 5: cli package | Member 5: detecting patterns. Member 2: detecting patterns. Member 1: detecting patterns.
Metrics | Member 1: gui package Member 2: logic package Member 3: model package Member 4: preferences package Member 5: cli package | Member 1: Doing the metrics