## Folha1
Sprint Backlog
Forecast | ToDo | In-Progress | Done | Review
Detect code smells | Member 4: Detect 3 code smells in preferences package and review 3 others | Member 2: Reviewing Member 3: Reviewing Member 4: Reviewing | Member 5: finished code smells. Member 1: finished code smells. Member 2: finished code smells. Member 3: finished code smells Member 4: finished code smells | Member 1: finished Reviews. Member 5: finished Reviews. Member 2: finished Reviews. Member 4: finished Reviews.
Use Case Diagrams | Member 1: gui package Member 2: logic package Member 3: model package Member 4: preferences package | Member 2: making diagrams Member 3: making diagrams Member 1: making diagram Member 4: making diagrams | Member 5: finished Use case diagrams
Design patterns | Member 4: detect 3 design patterns in preferences package and review 3 others | Member 3: doing the design patterns | Member 2: finished pattern detection Member 5: finished pattern detection Member 3: finished pattern detection Member 1: finished pattern detection Member 4: finished pattern detection | Member 5: finished Reviews. Member 1: finished Reviews. Member 2: finished Reviews. Member 4: finished Reviews
Metrics | Member 3: model package Member 4: do the MOOD metrics set, analyse the result and make a report. | Member 3: doing the metrics Member 4: doing the metrics | Member 5: finished doing the metrics Member 1: finished doing the metrics Member 2: finished doing the metrics Member 4: finished doing the metrics | Member 5: finished Reviews. Member 2: finished Reviews. Member 4: finished Reviews.